## Start
Lean Six Sigma Toolkit
Free templates by Greece Lean Six Sigma ¦ www.greeceleansixsigma.gr
How to use this toolkit
1. Start with the Project Charter (Define phase): problem, goal, scope and team.
2. Map the process at high level with SIPOC.
3. Use FMEA to rank risks: Severity x Occurrence x Detection = RPN (calculated automatically).
4. Hold the gains with the Control Plan (Control phase).
Cells with a light yellow fill are for your input. Row 1 of each table shows an example in grey italics: overwrite or delete it.
Light yellow = your input
> Project Charter
> SIPOC
> FMEA
> Control Plan
Need help? Lean Six Sigma Coach GPT, Green & Black Belt programs and project coaching: info@greeceleansixsigma.gr ¦ +30 231 231 5681

## Project Charter
DMAIC Project Charter
Free templates by Greece Lean Six Sigma ¦ www.greeceleansixsigma.gr
Field | Your project | Example
Project title |  | Reduce hotel check-in waiting time
Project leader (Belt) |  | Front Office Manager (Green Belt)
Sponsor / Champion |  | General Manager
Start date / target end date |  | 01/11 to 30/04
Business case (why now?) |  | Long waits at peak hours lower guest satisfaction scores and create overtime.
Problem statement (what, where, when, how much) |  | Between 15:00 and 18:00, 40% of guests wait more than 10 minutes to check in.
Goal statement (SMART) |  | Reduce the share of guests waiting more than 10 minutes to below 10% by 30/04.
Primary metric (Y) |  | % of guests waiting more than 10 minutes
Secondary / guardrail metrics |  | Guest satisfaction score, front office overtime hours
In scope |  | Check-in process for individual guests, 15:00 to 18:00
Out of scope |  | Group arrivals, online check-in system replacement
Team members & roles |  | Front office supervisor, housekeeping supervisor, IT analyst
Customers / stakeholders |  | Guests, front office team, housekeeping, revenue management
Expected benefits |  | Higher guest satisfaction, less overtime, smoother handover with housekeeping
Milestones (DMAIC) |  | Define 2 wks, Measure 4 wks, Analyze 4 wks, Improve 6 wks, Control 4 wks
Approvals (sponsor, date)

## SIPOC
SIPOC
Free templates by Greece Lean Six Sigma ¦ www.greeceleansixsigma.gr
Suppliers | Inputs | Process (5 to 7 high-level steps) | Outputs | Customers
Housekeeping | Clean-room status | 1. Guest arrives and queues | Room key and welcome | Guest
Tip: fill the Process column first, then Outputs and Customers, then Inputs and Suppliers.

## FMEA
FMEA
Free templates by Greece Lean Six Sigma ¦ www.greeceleansixsigma.gr
Process step | Potential failure mode | Potential effect(s) | Severity (1-10) | Potential cause(s) | Occurrence (1-10) | Current controls | Detection (1-10) | RPN | Recommended action | Owner / due date | S after | O after | D after | RPN after
Room assignment | Room not ready at check-in | Guest waits, complaint | 7 | No real-time room status from housekeeping | 6 | Phone calls to housekeeping | 5 | 210 | Introduce shared room-status board | HK supervisor, 15/12 | 7 | 3 | 2 | 42
RPN = Severity x Occurrence x Detection. Values 1 (best) to 10 (worst). Prioritise the highest RPN and any Severity of 9 or 10.

## Control Plan
Control Plan
Free templates by Greece Lean Six Sigma ¦ www.greeceleansixsigma.gr
Process step | Characteristic / KPI | Specification / target | Measurement method | Sample size & frequency | Responsible | Control method (chart, checklist, poka-yoke) | Reaction plan (what if out of control)
Check-in | % guests waiting > 10 min | < 10% | Queue timestamp in PMS | All arrivals, daily | Front Office Manager | Daily KPI board, weekly p-chart | Open second desk, escalate to duty manager